## Summary
Admissio Yield Forecaster: Technical RAID log
Risks | 8
High-rated risks | 5
Open or mitigating risks | 8
Assumptions | 5
Open issues | 3
Dependencies | 6
Scoring: Score = Likelihood x Impact. High is 6 or more, Medium 3 to 5, Low below 3.
Blue cells on the Risks sheet are inputs; edit them when a risk is reassessed at sprint review.
Baseline ratios in R1 and I4 come from python -m src.models.baseline on the 2024 IPEDS holdout.

## Risks
ID | Risk | Likelihood (1-3) | Impact (1-3) | Score | Rating | Owner | Mitigation | Sprint | Status
R1 | Forecast error stays higher for small, for-profit and HBCU institutions (baseline ratios 2.71, 3.81 and 1.39 against a 1.25 limit). | 3 | 3 | 9 | High | Analyst | Train on pooled peers with group-weighted loss, report Fairlearn group error at every run and block releases above 1.25. | Sprint 3 | Open
R2 | Three IPEDS years give too little history for per-institution time-series models. | 2 | 3 | 6 | High | Analyst | Pool institutions in one panel model and add earlier ADM releases if holdout error does not fall. | Sprint 2 | Open
R3 | Admission test policy changes (88 institutions in 2024) break historical yield patterns. | 2 | 2 | 4 | Medium | Analyst | Add a policy-change feature and report error separately for changed institutions. | Sprint 3 | Open
R4 | New IPEDS releases change headers, encodings or codes. | 3 | 2 | 6 | High | Analyst | Validate every load against the pandera schema in CI so drift fails the build. | Sprint 2 | Mitigating
R5 | Partner tenant data leak once Admissio aggregates enter the pipeline. | 1 | 3 | 3 | Medium | Product team | Aggregate inside each tenant, collect only counts, encrypt at rest in R2 and scope API keys per tenant. | Sprint 4 | Open
R6 | Offer plans used to cut places for under-resourced institutions. | 2 | 3 | 6 | High | Ethics Review Panel | Require named human approval of each offer plan and log every approval. | Sprint 4 | Open
R7 | Python models cannot run inside Cloudflare Workers. | 2 | 2 | 4 | Medium | Analyst | Serve precomputed forecasts and intervals as JSON from R2 through the Worker. | Sprint 4 | Open
R8 | One analyst cannot deliver pipeline, model and dashboard in four sprints. | 3 | 2 | 6 | High | Analyst | Prioritise tickets each sprint and defer dashboard extras before model or fairness work. | All | Open

## Assumptions
ID | Assumption | Validation | Owner | Validate by
A1 | Institution-level yield drivers in US data carry over structurally to Nigerian private universities until partner data exist. | Compare first partner cycles against forecasts before any production use. | Analyst | Sprint 5
A2 | NCES keeps publishing the admissions component annually in the same structure. | Schema checks in CI flag any change on load. | Analyst | Sprint 2
A3 | Institution-level aggregates are enough for offer planning without applicant records. | Confirm with admissions directors during the Sprint 4 review. | Product team | Sprint 4
A4 | Partners will share aggregated cycle counts under a data processing agreement. | Draft the agreement with the first partner's data protection lead. | Co-founder | Sprint 4
A5 | The Ethics Review Panel can review each sprint's release within one week. | Book review sessions at sprint planning. | Co-founder | All

## Issues
ID | Issue | Severity | Owner | Response | Status
I1 | Header spelling and text encodings differ between IPEDS files. | High | Analyst | read_ipeds_csv normalises headers and strips the byte-order mark. | Resolved
I2 | 89 records report applicants without usable admit or enrolment counts. | Medium | Analyst | Exclude from the yield target and keep for the demand model. | Open
I3 | Only two tribal colleges report, too few for group evaluation. | Medium | Analyst | Report the group as unassessed on the dashboard. | Open
I4 | The naive baseline already breaches the 1.25 fairness ratio for three groups. | High | Analyst | Treat as the Sprint 3 acceptance test for the new model. | Open
I5 | IPEDS splits the funnel by gender only, so applicant demographics cannot be audited. | Low | Analyst | Limit fairness claims to institution groups and state the limit in the model card. | Accepted

## Dependencies
ID | Dependency | Provider | Needed by | Contingency
D1 | IPEDS annual data releases | NCES (external) | Sprint 2 | Raw files committed and tagged, so work continues if the portal is down.
D2 | Cloudflare R2 and Workers on the Admissio account | Admissio product team | Sprint 4 | Provision a separate project namespace early.
D3 | Pinned Python libraries (pandas, LightGBM, Fairlearn, SHAP, MLflow) | Open-source maintainers | All | Versions pinned in requirements.txt and tested in CI.
D4 | Ethics Review Panel sign-off | Co-founder, partner data protection leads, external adviser | Sprints 3 to 5 | No release without sign-off.
D5 | Admissio tenant API exposing aggregated cycle counts | Admissio product team | Sprint 5 | IPEDS-only release proceeds if the API is late.
D6 | GitHub Actions continuous integration | GitHub | All | Tests run locally with pytest when CI is unavailable.